## Work Item Fields ROS-61
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Labels | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Outward issue link (Relates) | Custom field (Issue colour) | Custom field (Rank) | Custom field (Start date) | Status Category | Status Category Changed
Attaching an oversized file (100MB) at candidate creation causes the initial note to silently fail - but the candidate is still created, with a misleading technical error | ROS-61 | 10842 | Bug | Done | ROS | Roster - HR platform | software | Simona Rokaite | 70121:04f13a99-0a26-47e7-ab89-57351ce172e7 |  | Medium | Done | aydinkayusduru | 712020:35e8271d-9dca-4fe9-b6fa-e7c7fbd8c350 | Simona | 6178f6e7bcb574006888ac09 | Simona | 6178f6e7bcb574006888ac09 | 23/Jul/26 11:14 AM | 29/Jul/26 9:38 AM | 29/Jul/26 9:32 AM | 28/Jul/26 10:37 AM |  | 0 | bug | file-upload | *Severity:* High *Priority:* High *Steps to reproduce:* # Open "Add candidate" # Fill required fields, write an Initial note, and attach an oversized file (exceeding the 10MB limit) # Click Save *Expected:* If the attached file exceeds the size limit, the whole submission should be blocked upfront with a clear message ("File exceeds 10 MB limit") *Actual:* Two things happen: # *Candidate IS created and lands in Sourced* # *The initial note fails to save*, with the error toast showing the same raw technical message seen before: *"Candidate added, but the initial note failed to save - Body is disturbed or locked"* *Environment*: * Application: HR recruitment pipeline platform * Module: Candidate creation / file upload * User role: Recruiter Impact: * Candidate record is incomplete. * Poor user experience |  | Simona | 6178f6e7bcb574006888ac09 | [8 empty] | ROS-36 |  | 0¦i0015j:0000009 | 23/Jul/26 12:00 AM | Done | 28/Jul/26 10:37 AM

## Work Item Activity ROS-61
Type | Author | Date | Details
HISTORY | Simona | Wed Jul 29 06:38:11 UTC 2026 | Updated the Start date: None -> 23/Jul/26
HISTORY | Simona | Tue Jul 28 07:37:00 UTC 2026 | Changed the Status: In Review -> Done
HISTORY | Simona | Tue Jul 28 07:37:00 UTC 2026 | Updated the Resolution: None -> Done
HISTORY | Simona | Tue Jul 28 07:37:00 UTC 2026 | Updated the Rank: None -> Ranked higher
HISTORY | aydinkayusduru | Fri Jul 24 07:42:17 UTC 2026 | Changed the Status: In Progress -> In Review
HISTORY | aydinkayusduru | Fri Jul 24 07:42:16 UTC 2026 | Updated the Rank: None -> Ranked lower
HISTORY | aydinkayusduru | Fri Jul 24 07:23:57 UTC 2026 | Changed the Status: To Do -> In Progress
HISTORY | Simona | Thu Jul 23 11:03:06 UTC 2026 | Changed the Status: In Review -> To Do
HISTORY | Simona | Thu Jul 23 11:03:06 UTC 2026 | Updated the Rank: None -> Ranked higher
COMMENT | Simona | Thu Jul 23 11:03:00 UTC 2026 | [~accountid:712020:35e8271d-9dca-4fe9-b6fa-e7c7fbd8c350] Retested - this bug is only partially fixed. The size-limit/error-message issue was resolved in the *Add Candidate* flow. However, the same *"Body is disturbed or locked"* error still appears when attaching an oversized file via the *Notes tab on an existing candidate*. !Screenshot 2026-07-23 at 14.00.54.png¦width=633,alt="Screenshot 2026-07-23 at 14.00.54.png"!
HISTORY | Simona | Thu Jul 23 11:02:59 UTC 2026 | Added an Attachment: Screenshot 2026-07-23 at 14.00.54.png
HISTORY | aydinkayusduru | Thu Jul 23 09:33:10 UTC 2026 | Changed the Status: In Progress -> In Review
HISTORY | aydinkayusduru | Thu Jul 23 09:33:09 UTC 2026 | Updated the Rank: None -> Ranked higher
HISTORY | aydinkayusduru | Thu Jul 23 08:50:57 UTC 2026 | Changed the Status: To Do -> In Progress
HISTORY | Simona | Thu Jul 23 08:17:18 UTC 2026 | Updated the Link: None -> This work item relates to ROS-36
COMMENT | Simona | Thu Jul 23 08:17:00 UTC 2026 | Similar outcome when a big file is attached in Candidate Detail page - *“Body is disturbed or locked”*
HISTORY | Simona | Thu Jul 23 08:15:07 UTC 2026 | Added an Attachment: Screenshot 2026-07-23 at 11.13.03.png
HISTORY | Simona | Thu Jul 23 08:15:02 UTC 2026 | Updated the Description: *Steps to reproduce:* # Open "Add candidate" # Fill required fields, write an Initial note, and attach an oversized file # Click Save *Expected:* If the attached file exceeds the size limit, the whole submission should be blocked upfront with a clear message ("File exceeds 10 MB limit") *Actual:* Two things happen: # *Candidate IS created and lands in Sourced* # *The initial note fails to save*, with the error toast showing the same raw technical message seen before: *"Candidate added, but the initial note failed to save - Body is disturbed or locked"* -> *Severity:* High *Priority:* High *Steps to reproduce:* # Open "Add candidate" # Fill required fields, write an Initial note, and attach an oversized file (exceeding the 10MB limit) # Click Save *Expected:* If the attached file exceeds the size limit, the whole submission should be blocked upfront with a clear message ("File exceeds 10 MB limit") *Actual:* Two things happen: # *Candidate IS created and lands in Sourced* # *The initial note fails to save*, with the error toast showing the same raw technical message seen before: *"Candidate added, but the initial note failed to save - Body is disturbed or locked"* *Environment*: * Application: HR recruitment pipeline platform * Module: Candidate creation / file upload * User role: Recruiter Impact: * Candidate record is incomplete. * Poor user experience
HISTORY | Simona | Thu Jul 23 08:14:27 UTC 2026 | Updated the Labels: None -> bug file-upload
HISTORY | Simona | Thu Jul 23 08:14:17 UTC 2026 | Changed the Assignee: None -> aydinkayusduru
HISTORY | Simona | Thu Jul 23 08:14:05 UTC 2026 | Changed the Status: To Do -> To Do
HISTORY | Simona | Thu Jul 23 08:14:04 UTC 2026 | Created the Work item